## Slide 1
HARBORVIEW OFFICE OF INNOVATION & TECHNOLOGY
Executive
Status Report
Network Infrastructure • Projects • Operations
R. Lowery | Deputy Chief Networking Officer
Q3 2026 | Weekending September 30, 2026
Internal Use Only
1234 Harbor Boulevard, Harborview, PA • harborview.gov/oit

## Slide 2
HARBORVIEW OFFICE OF INNOVATION & TECHNOLOGY
Executive Summary
247
Q1 Network Tickets
Jan–Mar 2025
189
Q2 Tickets YTD
Apr–current
23
Single Points Failure
Identified
14
Monitoring Blind Spots
Now closed
32
Capacity Outages
Jan–current
50%
Outage Reduction Goal
Within 6 months
Leadership Readout
• Network capacity outages remain the highest-risk issue — direct impact on Public Safety dispatch and Harbor Airport operations.
• Current state assessment complete — 23 SPOFs and 14 monitoring blind spots identified and in remediation.
• Governance gap confirmed — no runbooks, no escalation matrix, no shift handoffs existed at start of engagement.
Immediate Executive Focus
RED
Resolve network capacity outages — Public Safety and Airport priority.
TRACK
Execute resiliency buildout — HA firewall and circuit redundancy.
MANDATE
Align all initiatives to Mayor Brayboy's Network Modernization Mandate.
Internal Use Only
Q3 2026 | Weekending September 30, 2026
02

## Slide 3
HARBORVIEW OFFICE OF INNOVATION & TECHNOLOGY
Agenda
01
Problem Statement & Current State
Network capacity crisis, governance gap, before picture
02
Mayoral & CIO Strategic Initiatives
Mayor Brayboy mandates, CIO Taylor alignment, named directives
03
Portfolio Status Map
All active initiatives — health indicators, owners, targets
04
Project Status — Red Indicators
Network Capacity Outages — full scorecard and recovery plan
05
Goals & Strategic Roadmap
Reliability, network buildout, capacity resolution — phased plan
06
Questions & Decisions
Executive actions required
Internal Use Only
Q3 2026 | Weekending September 30, 2026
03

## Slide 4
HARBORVIEW OFFICE OF INNOVATION & TECHNOLOGY
Problem Statement & Current State Assessment
The City of Harborview entered 2025 with a network environment operating without strategy, governance, or transparency. Chronic network capacity failures were causing active outages across Public Safety and Harbor International Airport. Critical initiatives were unmanaged due to a leadership staffing shortage. The sole operating objective was keeping the lights on.
32
Active Capacity
Outages
Jan–Mar 2025
23
Undocumented
Single Points Fail.
Identified Day 1
14
Monitoring
Blind Spots
Zero alerts
0
Runbooks /
Escalation Matrix
None existed
Governance Gap — Confirmed
• No network strategy aligned to CIO requirements
• No runbooks or documented escalation procedures
• No shift handoff standards — knowledge loss at every transition
• No project scorecard transparency — leadership operating blind
• Critical initiatives stalled — staffing shortage unaddressed
Highest Impact — Confirmed Stakeholders
CRITICAL
Public Safety Dispatch — Network outages disrupting 911 routing
CRITICAL
Harbor International Airport — Circuit failures — intermittent connectivity
HIGH
75 City Departments — No communication — no escalation path
HIGH
CIO Office — No visibility into network posture or risk
Internal Use Only
Q3 2026 | Weekending September 30, 2026
04

## Slide 5
HARBORVIEW OFFICE OF INNOVATION & TECHNOLOGY
Mayoral & CIO Strategic Initiatives
Mayor Minerva Brayboy | Network Modernization Mandate — Issued January 2025 | CIO Janelle Taylor — Strategic Alignment Owner
Mayoral Directives
ACTIVE
M-01 Network Resiliency Initiative
Eliminate single points of failure citywide — Public Safety and Airport first
ACTIVE
M-02 Network Availability Mandate
99.99% availability target — Public Safety and Airport — 24/7 operational standard
PLAN
M-03 Digital Equity — ConnectHarborview
Broadband expansion — underserved neighborhoods — Phase 1 scoping Q2 2025
RED
M-04 Public Safety Network Upgrade
Capacity outages actively impacting dispatch — Mayoral priority — immediate resolution required
CIO Strategic Initiatives — Janelle Taylor
ACTIVE
C-01 Network Process Improvement
Standardized runbooks, escalation matrix, shift handoffs — 30-day delivery
ACTIVE
C-02 Network Technology Strategy
Full strategy aligned to Mayoral mandates — R. Lowery lead — Q2 delivery
PLAN
C-03 Copper-to-Fiber Migration
17 remote City facilities — assessment complete — migration Phase 1 Q3 2025
PLAN
C-04 NIST 800-53 Network Compliance
Gap assessment complete — remediation roadmap — 80% compliance target 12 months
Internal Use Only
Q3 2026 | Weekending September 30, 2026
05

## Slide 6
HARBORVIEW OFFICE OF INNOVATION & TECHNOLOGY
Portfolio Status Map
Mayoral Portfolio
RED
Network Capacity Outages
Active — Day 1
Immediate
ACTIVE
Network Resiliency Initiative
In progress
Q1–Q2 2025
ACTIVE
Public Safety Network Upgrade
In progress
Q1–Q2 2025
PLAN
ConnectHarborview Broadband
Scoping Q2
Q2–Q3 2025
HOLD
Legacy System Replacement
Post-stabilization
Q2–Q3 2025
RISK
Harbor Airport Connectivity
Monitoring
Q2–Q3 2025
CIO Strategic Portfolio
ACTIVE
Network Process Improvement
30-day delivery
ACTIVE
Network Technology Strategy
Q2 2025
ACTIVE
Monitoring Coverage Expansion
Complete
PLAN
Copper-to-Fiber Migration
Phase 1 Q3 2025
PLAN
NIST 800-53 Compliance
12-month roadmap
HOLD
SD-WAN Deployment
Post-stabilization
Internal Use Only
Q3 2026 | Weekending September 30, 2026
06

## Slide 7
HARBORVIEW OFFICE OF INNOVATION & TECHNOLOGY
Project Status
Red indicators — full scorecard
Internal Use Only
1234 Harbor Boulevard, Harborview, PA • harborview.gov/oit

## Slide 8
HARBORVIEW OFFICE OF INNOVATION & TECHNOLOGY
Major Project Dashboard
Project
Health
Lifecycle
Executive Sponsor / Owner
Target
Network Capacity Outages — Public Safety
RED
Active Response
Mayor Brayboy / R. Lowery
Q2 2025
Harbor Airport Circuit Restoration
RED
Remediation
CIO Taylor / R. Lowery
Apr 2025
Network Resiliency — HA Firewall Deploy
TRACK
In Progress
CIO Taylor
Q2 2025
Monitoring Coverage — Blind Spot Closure
COMPLETE
Complete
R. Lowery
Mar 2025
Network Process Improvement
ACTIVE
In Progress
R. Lowery
Apr 2025
Copper-to-Fiber — Remote Facilities
PLAN
Assessment
CIO Taylor / R. Lowery
Q3 2025
NIST 800-53 Network Compliance
PLAN
Gap Assessment
CISO / R. Lowery
Q1 2026
SD-WAN Deployment
HOLD
On Hold
CIO Taylor
TBD
Internal Use Only
Q3 2026 | Weekending September 30, 2026
08

## Slide 9
HARBORVIEW OFFICE OF INNOVATION & TECHNOLOGY | RED PROJECT SCORECARD
Network Capacity Outages — Public Safety & Airport
RED
Target Completion
Q2 2025 — June 30
Executive Sponsor
Mayor Minerva Brayboy
Initiative Owner
R. Lowery, Deputy CNO
Lifecycle Phase
Active Response / Remediation
Summary / Scope:
Ongoing network capacity failures causing active service outages at Public Safety Dispatch (911 routing impacted) and Harbor International Airport. Root cause: aging WAN infrastructure, no circuit redundancy, bandwidth saturation at peak load. Mayoral directive issued January 2025. Immediate remediation required.
IT Assigned Resources — Role — Allocation
R. Lowery
Deputy CNO — Executive Lead
100%
A. Salado
Senior Network Engineer — WAN Lead
90%
S. Youngblood
Network Engineer — Circuit Analysis
80%
D. Caldwell
NOC Lead — Monitoring
75%
A. Romano
PM/BA — Coordination
60%
Major Risks
1. 911 routing degradation during peak capacity events — life safety impact if not resolved before Q2.
2. Airport connectivity failure during weather or surge events — single carrier, no backup circuit.
3. Budget approval for circuit upgrades pending — delay extends outage exposure beyond Q2 target.
4. Senior engineer bandwidth — 3 of 5 assigned engineers simultaneously supporting other P1 events.
Task / Activity
Owner
Status
Target
WAN bandwidth assessment — Tier 1
A. Salado
✓ Complete
Mar 15
Secondary circuit — Public Safety HQ
R. Lowery
In Progress
Apr 15
Circuit failover test — Public Safety
S. Youngblood
Scheduled
Apr 22
Airport backup circuit activation
A. Salado
In Progress
May 1
NOC capacity threshold alerting
D. Caldwell
✓ Complete
Mar 28
Internal Use Only
Q3 2026 | Weekending September 30, 2026
09

## Slide 10
HARBORVIEW OFFICE OF INNOVATION & TECHNOLOGY
Goals & Strategic Roadmap
01
Increased Network Reliability
Eliminate all 23 confirmed SPOFs. Achieve 99.99% availability — Public Safety and Airport. Establish 24/7 NOC monitoring coverage at 100%.
02
Resolve Network Capacity Crisis
Close all 32 active outage events. Deploy secondary circuits at all Tier 1 locations. Implement capacity monitoring and auto-alerting by Q2 2025.
03
Network Buildout & Modernization
Execute copper-to-fiber migration across 17 remote facilities. Deploy SD-WAN at Tier 1 and 2 locations. Expand managed device coverage citywide.
04
Governance & Transparency
Full runbook library. Standardized escalation matrix. Shift handoff compliance 100%. Monthly scorecard reporting to CIO and Deputy CIOs.
Internal Use Only
Q3 2026 | Weekending September 30, 2026
10

## Slide 11
Questions & Decisions Required
DECISION
Budget approval — secondary circuit procurement — Public Safety HQ and Airport — est. $480K — CIO Taylor / Mayor Brayboy
DECISION
Emergency staffing authorization — 2 senior network engineers — contract support — 6-month engagement to close capacity gap
APPROVE
Network Technology Strategy — Q2 2025 delivery — CIO approval required to proceed to Mayoral briefing
APPROVE
Copper-to-fiber migration Phase 1 scope and budget — 17 facilities — est. $1.2M capital — Q3 2025 start
R. Lowery | Deputy Chief Networking Officer | City of Harborview OIT
Internal Use Only
Q3 2026 | Weekending September 30, 2026
11