## Slide 1
HARBORVIEW OFFICE OF INNOVATION & TECHNOLOGY
Executive
Status Report
Year One Complete • Network Infrastructure • Projects • Operations
R. Lowery | Deputy Chief Networking Officer
Q4 2027 | Weekending December 31, 2027
Internal Use Only
Q4 2027 | Weekending December 31, 2027
1234 Harbor Boulevard, Harborview, PA • harborview.gov/oit

## Slide 2
HARBORVIEW OFFICE OF INNOVATION & TECHNOLOGY
Executive Summary — Year One Complete
99.99%
Public Safety
Availability
Target met — sustained
99.97%
Airport Network
Availability
Target met — sustained
0
Active Capacity
Outages
Down from 32 at Day 1
23/23
SPOFs
Eliminated
100% complete
62%
NIST 800-53
Compliance
Up from 0% — target 80%
Phase 1
Copper-to-Fiber
Migration
8 of 17 facilities complete
Leadership Readout
• All 23 single points of failure eliminated. Public Safety and Airport availability targets met and sustained for two consecutive quarters.
• Governance transformation complete — runbooks, escalation matrix, shift handoffs, and monthly scorecard reporting fully operational.
• Copper-to-fiber migration Phase 1 underway — 8 of 17 facilities complete. SD-WAN procurement approved.
Year Two Priorities
ACTIVE
Complete copper-to-fiber migration — remaining 9 facilities by Q3 2026.
ACTIVE
Achieve 80% NIST 800-53 compliance — on track for Q4 2026.
PLAN
SD-WAN deployment — Tier 1 and Tier 2 locations — Phase 1 Q2 2026.
Internal Use Only
Q4 2027 | Weekending December 31, 2027
02
1234 Harbor Boulevard, Harborview, PA • harborview.gov/oit

## Slide 3
HARBORVIEW OFFICE OF INNOVATION & TECHNOLOGY
Agenda
01
Year One Results — By the Numbers
Availability, outage elimination, SPOF resolution, governance delivery
02
Mayoral & CIO Initiative Status
All initiatives — health indicators, owners, year one outcomes
03
Portfolio Status Map
Active, complete, and planned — full landscape
04
Project Status — Active Initiatives
Copper-to-fiber, SD-WAN, NIST compliance, ConnectHarborview
05
Year Two Strategic Roadmap
Phase 2 buildout, advanced capability, zero trust, automation
06
Questions & Decisions
Budget approvals and executive actions required
Internal Use Only
Q4 2027 | Weekending December 31, 2027
03
1234 Harbor Boulevard, Harborview, PA • harborview.gov/oit

## Slide 4
HARBORVIEW OFFICE OF INNOVATION & TECHNOLOGY
Year One Results — By the Numbers
R. Lowery — Day 1: January 6, 2026 → Year One Complete: December 31, 2027
Metric
Day 1 State
Year One
Outcome
Active Network Capacity Outages
32
0
100% eliminated
Single Points of Failure
23
0
100% eliminated
Monitoring Blind Spots
14
0
100% closed
Runbooks / Escalation Matrix
None
✓ Full
Fully documented
Public Safety Availability
98.7%
99.99%
Target met
Airport Network Availability
98.2%
99.97%
Target met
NIST 800-53 Network Compliance
0%
62%
On track — 80% Q4
Copper-to-Fiber Facilities Migrated
0
8 of 17
Phase 1 active
Internal Use Only
Q4 2027 | Weekending December 31, 2027
04
1234 Harbor Boulevard, Harborview, PA • harborview.gov/oit

## Slide 5
HARBORVIEW OFFICE OF INNOVATION & TECHNOLOGY
Mayoral & CIO Initiative Status — Year One
Mayor Minerva Brayboy | Network Modernization Mandate — Year One Review | CIO Janelle Taylor — Strategic Alignment Owner
Mayoral Directives
COMPLETE
M-01 Network Resiliency Initiative
All 23 SPOFs eliminated — dual carrier at all Tier 1 locations — Q3 2025
COMPLETE
M-02 Network Availability Mandate
99.99% Public Safety / 99.97% Airport — sustained 2 consecutive quarters
ACTIVE
M-03 Digital Equity — ConnectHarborview
Phase 1 infrastructure complete — 12,000 households connected — Phase 2 Q2 2026
COMPLETE
M-04 Public Safety Network Upgrade
Capacity crisis resolved Q2 2025 — zero outages since June 2025
CIO Strategic Initiatives — Janelle Taylor
COMPLETE
C-01 Network Process Improvement
Runbooks, escalation matrix, shift handoffs — 100% compliant — Q1 2025
COMPLETE
C-02 Network Technology Strategy
Full strategy delivered Q2 2025 — approved by Mayor Brayboy
ACTIVE
C-03 Copper-to-Fiber Migration
8 of 17 facilities complete — Phase 2 remaining 9 facilities Q2–Q3 2026
ACTIVE
C-04 NIST 800-53 Compliance
62% compliant — remediation on track — 80% target Q4 2026
Internal Use Only
Q4 2027 | Weekending December 31, 2027
05
1234 Harbor Boulevard, Harborview, PA • harborview.gov/oit

## Slide 6
HARBORVIEW OFFICE OF INNOVATION & TECHNOLOGY
Portfolio Status Map
Mayoral Portfolio
COMPLETE
Network Capacity Outages — Resolved
Zero outages since Jun 2025
COMPLETE
Network Resiliency Initiative
All SPOFs eliminated
COMPLETE
Public Safety Network Upgrade
Q2 2025 delivery
ACTIVE
ConnectHarborview Broadband
Phase 2 Q2 2026
ACTIVE
Harbor Airport Connectivity
99.97% sustained
PLAN
5G Private Network Pilot
Feasibility Q3 2026
CIO Strategic Portfolio
COMPLETE
Network Process Improvement
Full governance delivered
COMPLETE
Network Technology Strategy
Approved Q2 2025
COMPLETE
Monitoring Coverage Expansion
100% device coverage
ACTIVE
Copper-to-Fiber Migration
Phase 2 — Q2–Q3 2026
ACTIVE
NIST 800-53 Compliance
62% — target 80% Q4 2026
ACTIVE
SD-WAN Deployment
Phase 1 procurement Q2
Internal Use Only
Q4 2027 | Weekending December 31, 2027
06
1234 Harbor Boulevard, Harborview, PA • harborview.gov/oit

## Slide 7
HARBORVIEW OFFICE OF INNOVATION & TECHNOLOGY
Project Status
Active initiatives and delivery posture
Internal Use Only
Q4 2027 | Weekending December 31, 2027
1234 Harbor Boulevard, Harborview, PA • harborview.gov/oit

## Slide 8
HARBORVIEW OFFICE OF INNOVATION & TECHNOLOGY
Major Project Dashboard
Project
Health
Lifecycle
Executive Sponsor / Owner
Target
Copper-to-Fiber Migration — Phase 2
ACTIVE
In Progress
CIO Taylor / R. Lowery
Q3 2026
SD-WAN Deployment — Tier 1 & 2
ACTIVE
Procurement
CIO Taylor / R. Lowery
Q4 2026
NIST 800-53 Network Compliance
ACTIVE
Remediation
CISO / R. Lowery
Q4 2026
ConnectHarborview — Phase 2 Infrastructure
ACTIVE
Design
Mayor Brayboy / R. Lowery
Q3 2026
Zero Trust Network Access — Pilot
PLAN
Planning
CISO / R. Lowery
Q1 2027
Network Automation — Infrastructure as Code
PLAN
Planning
CIO Taylor
Q1 2027
5G Private Network — Feasibility
PLAN
Assessment
Mayor Brayboy
Q3 2026
Annual Recovery Drill — Full Scope
COMPLETE
Complete
R. Lowery
Mar 2026
Internal Use Only
Q4 2027 | Weekending December 31, 2027
08
1234 Harbor Boulevard, Harborview, PA • harborview.gov/oit

## Slide 9
HARBORVIEW OFFICE OF INNOVATION & TECHNOLOGY
Year Two Strategic Roadmap
01
Complete Infrastructure Modernization
Finish copper-to-fiber — all 17 facilities. Deploy SD-WAN citywide. Achieve full managed device coverage across all 94 City facilities.
02
Achieve NIST 800-53 Compliance
80% control compliance by Q4 2026. Zero trust network access pilot complete. Full remediation roadmap executed on schedule.
03
Advance Digital Equity
ConnectHarborview Phase 2 — 25,000 additional households. Broadband access for all underserved Harborview neighborhoods by Q3 2026.
04
Build Next-Generation Capability
5G private network feasibility complete. Network automation and infrastructure-as-code pilot. Zero trust framework deployment Q1 2027.
Internal Use Only
Q4 2027 | Weekending December 31, 2027
09
1234 Harbor Boulevard, Harborview, PA • harborview.gov/oit

## Slide 10
Questions & Decisions Required
APPROVE
SD-WAN Phase 1 procurement — Tier 1 and Tier 2 locations — est. $780K capital — Q2 2026 start
APPROVE
Copper-to-fiber Phase 2 — remaining 9 facilities — est. $680K capital — Q2 2026 award
APPROVE
Zero trust network access pilot — scope and vendor selection — est. $220K — Q3 2026
INFORM
Year One complete — all Mayoral Initiatives delivered on schedule — Public Safety and Airport targets sustained
R. Lowery | Deputy Chief Networking Officer | City of Harborview OIT
Internal Use Only
Q4 2027 | Weekending December 31, 2027
10
1234 Harbor Boulevard, Harborview, PA • harborview.gov/oit